## Slide 1
Philosophy
  Pragmatism Paradigm
Approach
  Abductive Approach
Strategy
  Multi Methodological Strategy
Methods
  Interviews and Surveys
  Monte Carlo Analysis
Risk Management in Construction of Megahousing Projects in Egypt
Mohamed Ibrahim1,2, George Ofori1, Maged Morcos2
1School of Built Environment and Architecture, London South Bank University, 103 Borough Road, London SE1 0AA, United Kingdom 2Department of Civil Engineering, The British University in Egypt, El-Sherouk City, Cairo, Egypt
Motivation
Slum Urbanisation Crisis
Constructed with 95% delays, high cost, and poor quality buildings.
Slum vs. Mega Housing
Recently, Egypt strategy 2030 is targeting successful delivery of mega housing.
Risk management framework is an ideal solution to reduce the impact on delivery of mega housing projects
Risk Management Framework is developed using the Risk Management Standard ISO 31000
Methodology
Conclusions
Researcher Contacts
M.ASCE – Member of the American Society of Civil Engineers, USA.
MAPM – Member of the Association of Project Management, UK.
Results
Aim
Low risk knowledge was observed, 45% of project team do not participate in the process of risk management.
Monte Carlo highlighted that $273,000 are to be added to the construction budget.
Risk categories included
financial risks, safety risks, and
government support risks.
The Risk framework is in line with the
International Standardaisation (ISO31000).
The cost of a Mega housing project in Egypt “New Capital” ranged between $125,687,351 and $126,183,808. After implementing mitigations the cost ranged between $125,687,351 and 125,917,868 this means that the maximum completion cost is reduced by an amount of $265,940. This reduction is due to the implemented responsive actions.
Qualitative risks are identified using interviews. Survey results allowed the recognition of impact scales. Monte Carlo analysed the impact of risks on delivery time and cost.
To develop a risk management framework to improve risk management practices and success in delivery during construction of Mega housing projects in Egypt.
Researcher Mail: Ibrahm63@lsbu.ac.uk
For better future in delivery of mega housing projects.
For better EGYPT
Respondents
Low
Medium
High
Risk Knowledge
Risk Management Framework
Step 1
identify Risks
Step 2
Analyse
Step 5
Report
Step 4
Monitor
Step 3
Respond